## Master Plan
🎣 VisBait — Complete Launch Roadmap ¦ Updated April 2025 ¦ Web Live by June 1, 2025
✅ = Complete ¦ 🔴 Critical = blocks everything, do today ¦ 🟠 High = must finish before June ¦ 🟡 Medium = finish in June ¦ 🟢 Low = post-June
CURRENT STATUS: ✅ Email set up ✅ Google Voice set up ✅ Instagram secured ✅ TikTok secured ✅ YouTube secured ⬜ Domain ⬜ LLC ⬜ EIN ⬜ Bank
# | Sprint / Week | Task | Detail / Notes | Category | Priority | Est. Cost | Target Date | Status | Owner | Done Date | Next Step / Notes
ALREADY DONE · Completed This Week
1 | ALREADY DONE | Set up VisBait business email | Business email created and active. Use for ALL VisBait registrations going forward | Operations | Critical | $0 | ✅ Done | ✅ Done
2 | ALREADY DONE | Set up Google Voice business number | Free business phone number. Never give out personal cell for VisBait | Operations | Critical | $0 | ✅ Done | ✅ Done
3 | ALREADY DONE | Secure @VisBait on Instagram | Handle locked. Keep login saved in password manager | Marketing | Critical | $0 | ✅ Done | ✅ Done
4 | ALREADY DONE | Secure @VisBait on TikTok | Handle locked. Keep login saved in password manager | Marketing | Critical | $0 | ✅ Done | ✅ Done
5 | ALREADY DONE | Secure VisBait on YouTube | Channel created. Keep login saved in password manager | Marketing | Critical | $0 | ✅ Done | ✅ Done
TODAY · Do Right Now — Takes 70 Minutes Total
6 | TODAY | Secure @VisBait on X (Twitter) | x.com → Sign Up → username: visbait. If taken try visbaitapp. Use VisBait email | Marketing | Critical | $0 | Today | ⬜ Not Started
7 | TODAY | Secure VisBait Page on Facebook | facebook.com → Create a Page → Category: App or Software → Name: VisBait. NOT a personal profile | Marketing | Critical | $0 | Today | ⬜ Not Started
8 | TODAY | Secure VisBait on Pinterest | pinterest.com → Sign Up → Business Account → Name: VisBait. Use VisBait email | Marketing | Critical | $0 | Today | ⬜ Not Started
9 | TODAY | Search 'VisBait' on USPTO TESS | tmsearch.uspto.gov → Basic Word Mark Search → search VisBait + Vis Bait + VizBait. Screenshot results. Takes 15 min | Legal | Critical | $0 | Today | ⬜ Not Started
10 | TODAY | Search 'VisBait' on PA business DB | apps.dos.pa.gov → confirm name not already taken before paying LLC fee. Takes 5 min | Legal | Critical | $0 | Today | ⬜ Not Started
11 | TODAY | Buy visbait.com on Namecheap | namecheap.com → search visbait.com → add to cart → ENABLE WhoisGuard (free, hides your address) → pay ~$14 | Branding | Critical | $14 | Today | ⬜ Not Started
12 | TODAY | Also grab visbait.app if available | Check during Namecheap checkout. If under $20 grab it. Protects the brand across extensions | Branding | High | $15 | Today | ⬜ Not Started
13 | TODAY | File PA LLC — Certificate of Organization | file.dos.pa.gov → Create a Business → Domestic LLC → Name: VisBait LLC → Registered agent: YOUR name + Philly address → Purpose: 'any lawful purpose' → Pay $125 | Legal | Critical | $125 | Today | ⬜ Not Started
14 | TODAY | Get EIN from IRS immediately after LLC | irs.gov EIN online application → LLC → 1 member → Pennsylvania → Started new business → SCREENSHOT THE EIN — not emailed to you | Legal | Critical | $0 | Today | ⬜ Not Started
15 | TODAY | Apply for Mercury business bank account | mercury.com → LLC → enter EIN + LLC name + your info → upload ID → upload LLC cert when it arrives (3–7 days). Free, no minimums | Financial | Critical | $0 | Today | ⬜ Not Started
WEEK 1 · Jan 27 – Feb 2 · FINISH LEGAL FOUNDATION
16 | WEEK 1 | Receive LLC Certificate PDF from PA | PA emails the official certificate within 3–7 business days. Save it — you need it for Mercury bank and trademark filing | Legal | Critical | $0 | Feb 2 | ⬜ Not Started
17 | WEEK 1 | Upload LLC Certificate to Mercury | Log back into Mercury and upload the PDF once received. This completes your bank account activation | Financial | Critical | $0 | Feb 2 | ⬜ Not Started
18 | WEEK 1 | Set up Wave accounting (free) | wave.com → free bookkeeping. Log every expense from Day 1 — domain, LLC fee, software. All tax deductible | Financial | High | $0 | Feb 1 | ⬜ Not Started
19 | WEEK 1 | Log all expenses so far into Wave | Enter: email service, Google Voice (free), Instagram/TikTok/YT signups (free), domain $14, LLC $125 into Wave from Day 1 | Financial | High | $0 | Feb 1 | ⬜ Not Started
20 | WEEK 1 | Set up Google Workspace email | workspace.google.com → connect visbait.com domain → create yourname@visbait.com → $6/month paid from Mercury | Operations | High | $72/yr | Feb 2 | ⬜ Not Started
21 | WEEK 1 | Register for PA state taxes on myPATH | mypath.pa.gov → register LLC for Pennsylvania state taxes. Required before any revenue | Legal | High | $0 | Feb 2 | ⬜ Not Started
22 | WEEK 1 | Write down all passwords in one place | Use a password manager (Bitwarden is free) or a secure document. You now have 8+ accounts — do not lose access | Operations | High | $0 | Feb 1 | ⬜ Not Started
WEEK 2 · Feb 3 – Feb 9 · GET THE SITE LIVE
23 | WEEK 2 | Create GitHub account | github.com → Sign Up → use VisBait email → choose a clean username | Hosting | Critical | $0 | Feb 3 | ⬜ Not Started
24 | WEEK 2 | Create 'visbait' public repository | New repo → name: visbait → public → initialize with README. This is where all your code lives | Hosting | Critical | $0 | Feb 3 | ⬜ Not Started
25 | WEEK 2 | Rename visbait.html to index.html | GitHub Pages REQUIRES the file to be named index.html. Open the file, Save As index.html | Hosting | Critical | $0 | Feb 3 | ⬜ Not Started
26 | WEEK 2 | Upload index.html to GitHub repo | In the repo click 'Add file' → 'Upload files' → drag in index.html → click 'Commit changes' | Hosting | Critical | $0 | Feb 3 | ⬜ Not Started
27 | WEEK 2 | Enable GitHub Pages | Repo → Settings → Pages → Source: Deploy from branch → Branch: main → folder: / (root) → Save. Site is live in 2 minutes | Hosting | Critical | $0 | Feb 3 | ⬜ Not Started
28 | WEEK 2 | Confirm site loads at github.io URL | Visit yourusername.github.io/visbait — test on desktop AND phone. All tabs should work. Fix any broken features | Hosting | Critical | $0 | Feb 3 | ⬜ Not Started
29 | WEEK 2 | Create free Cloudflare account | cloudflare.com → Add your visbait.com domain → it auto-scans your DNS records | Security | Critical | $0 | Feb 4 | ⬜ Not Started
30 | WEEK 2 | Point visbait.com to GitHub Pages | In Cloudflare DNS → Add CNAME record → Name: www → Target: yourusername.github.io → Save | Hosting | Critical | $0 | Feb 4 | ⬜ Not Started
31 | WEEK 2 | Enable HTTPS in Cloudflare | SSL/TLS → set to Full (Strict). Edge Certificates → toggle 'Always Use HTTPS' ON. Takes effect within minutes | Security | Critical | $0 | Feb 4 | ⬜ Not Started
32 | WEEK 2 | Confirm visbait.com loads with HTTPS | Visit https://visbait.com — padlock must appear in browser. If not wait 30 min and check again | Hosting | Critical | $0 | Feb 5 | ⬜ Not Started
33 | WEEK 2 | Restrict Google Maps API key | Google Cloud Console → APIs & Services → Credentials → your key → Application restrictions → HTTP referrers → add visbait.com/* | Security | Critical | $0 | Feb 5 | ⬜ Not Started
34 | WEEK 2 | Add Cloudflare security headers | Cloudflare → Rules → Transform Rules → Modify Response Headers. Add: X-Frame-Options: DENY, X-Content-Type-Options: nosniff | Security | High | $0 | Feb 5 | ⬜ Not Started
35 | WEEK 2 | Enable Cloudflare rate limiting | Cloudflare → Security → WAF → Rate Limiting → block IPs making >100 requests/minute | Security | High | $0 | Feb 5 | ⬜ Not Started
36 | WEEK 2 | Test site on real iPhone and Android | Not just desktop Chrome. Real mobile testing catches layout bugs, slow loads, tap issues. Fix what you find | Product | High | $0 | Feb 7 | ⬜ Not Started
WEEK 3 · Feb 10 – Feb 16 · LEGAL DOCS — Must exist before any stranger uses the site
37 | WEEK 3 | Generate Privacy Policy on Termly.io | termly.io → free → must cover: what you collect, location data, user deletion rights, GDPR, CCPA, no data sales | Legal | Critical | $0 | Feb 10 | ⬜ Not Started
38 | WEEK 3 | Generate Terms of Service on Termly.io | Must include: platform not seller (Section 230), age 13+ COPPA gate, arbitration clause, Pennsylvania governing law | Legal | Critical | $0 | Feb 10 | ⬜ Not Started
39 | WEEK 3 | Add Privacy Policy link to site footer | Must be visible on every page. Add a footer to index.html with links to both legal documents | Legal | Critical | $0 | Feb 11 | ⬜ Not Started
40 | WEEK 3 | Add Terms of Service link to site footer | Same footer as above. Users must be able to find ToS before creating an account | Legal | Critical | $0 | Feb 11 | ⬜ Not Started
41 | WEEK 3 | Add Termly cookie consent banner | Add Termly widget script tag to index.html <head>. Must appear before any EU or California user accesses the site | Legal | Critical | $0 | Feb 11 | ⬜ Not Started
42 | WEEK 3 | Add 'Do Not Sell My Data' link | Required by CCPA for California users. Add to footer. Links to a simple page stating you do not sell personal data | Legal | Critical | $0 | Feb 11 | ⬜ Not Started
43 | WEEK 3 | Add fishing disclaimer to map and tips | 'Always verify local fishing regulations. VisBait is not responsible for regulatory compliance.' Add to map section | Legal | High | $0 | Feb 12 | ⬜ Not Started
44 | WEEK 3 | Register DMCA agent with Copyright Office | dmca.copyright.gov/osp → $6/year → required by law to maintain Section 230 protection for user-uploaded content | Legal | High | $6/yr | Feb 14 | ⬜ Not Started
45 | WEEK 3 | Write 1-page Incident Response Plan | Simple doc: if we get hacked — who to notify, how to reset, how to contact users. NIST requires this exist | Security | High | $0 | Feb 16 | ⬜ Not Started
46 | WEEK 3 | Draft Operating Agreement for LLC | Solo founder: states you are sole member and owner. Template at Northwest Registered Agent (free). Save as PDF | Legal | High | $0 | Feb 16 | ⬜ Not Started
WEEK 4 · Feb 17 – Feb 23 · REAL BACKEND — Replace mock data with real database
47 | WEEK 4 | Create Supabase account | supabase.com → Start for free → no credit card. Free tier: 500MB database, 50,000 monthly users, auth included | Backend | Critical | $0 | Feb 17 | ⬜ Not Started
48 | WEEK 4 | Create database tables in Supabase | Create tables: users, posts, catches, map_pins, achievements, messages, groups, listings, comments, reactions | Backend | Critical | $0 | Feb 17–18 | ⬜ Not Started
49 | WEEK 4 | Set up Supabase Auth | Supabase dashboard → Auth → Settings. Enable: email/password, Google OAuth. Require email verification. Min password: 12 chars | Backend | Critical | $0 | Feb 18 | ⬜ Not Started
50 | WEEK 4 | Add real user signup + login to app | Replace mock profile with Supabase auth. Users can register with email, verify, and log in. Store session in localStorage | Product | Critical | $0 | Feb 18–20 | ⬜ Not Started
51 | WEEK 4 | Connect map pins to database | New pins save to Supabase map_pins table with lat/lng, notes, type, user_id. Load all pins on map open | Product | Critical | $0 | Feb 20–22 | ⬜ Not Started
52 | WEEK 4 | Add Supabase Storage for image upload | Supabase → Storage → create bucket: 'posts'. Wire upload form to actually save images. 1GB free | Product | High | $0 | Feb 22–23 | ⬜ Not Started
53 | WEEK 4 | Replace mock weather with real API | openweathermap.org → free API key → 1,000 calls/day free → replace hardcoded weather card with real current conditions | Product | High | $0 | Feb 22–23 | ⬜ Not Started
54 | WEEK 4 | Sanitize all user text inputs | Strip HTML/JS from every text field before saving or displaying. Prevents XSS. Do on frontend AND in Supabase functions | Security | Critical | $0 | Feb 23 | ⬜ Not Started
WEEK 5–6 · Feb 24 – Mar 9 · CORE PRODUCT — Wire everything to real data
55 | WEEK 5–6 | Wire up real post creation and feed | Posts save to Supabase posts table. Feed queries real posts ordered by date. Like/dislike counts persist in DB | Product | Critical | $0 | Feb 24–28 | ⬜ Not Started
56 | WEEK 5–6 | Wire up real reel uploads | Video saves to Supabase Storage. Reels feed loads real videos from DB. Comments save and load from comments table | Product | Critical | $0 | Mar 1–3 | ⬜ Not Started
57 | WEEK 5–6 | Wire up real DMs and group messages | Messages save to messages table. Use Supabase Realtime for live message delivery without page refresh | Product | High | $0 | Mar 3–5 | ⬜ Not Started
58 | WEEK 5–6 | Wire up achievement tracking logic | Server-side logic: when catch weight > 10lbs → unlock 'Double Digit Monster'. Trigger on catch save via Supabase function | Product | High | $0 | Mar 5–7 | ⬜ Not Started
59 | WEEK 5–6 | Wire up marketplace listings to DB | Listings save to listings table. Proximity filter uses user's stored lat/lng. Category filter queries by type column | Product | High | $0 | Mar 7–9 | ⬜ Not Started
60 | WEEK 5–6 | Add Stripe Connect for marketplace | stripe.com/connect → handles payments → you take 6% cut → test in Stripe sandbox first before going live | Revenue | High | 2.9%+$0.30 | Mar 7–9 | ⬜ Not Started
61 | WEEK 5–6 | Set up Resend for email notifications | resend.com → 3,000 emails/month free → welcome email, achievement unlock notification, new message alert | Product | Medium | $0 | Mar 8–9 | ⬜ Not Started
62 | WEEK 5–6 | Run OWASP ZAP security scan | Download OWASP ZAP free. Scan https://visbait.com. Fix ALL High-severity findings before inviting any users | Security | Critical | $0 | Mar 9 | ⬜ Not Started
WEEK 7–8 · Mar 10 – Mar 23 · IP PROTECTION — Before any press or outreach
63 | WEEK 7–8 | File USPTO trademark — Class 42 (Tech) | uspto.gov → TEAS Plus ($250) → Class 42: 'Online social media platform for fishing enthusiasts; software as a service' | IP | Critical | $250 | Mar 10 | ⬜ Not Started
64 | WEEK 7–8 | File USPTO trademark — Class 35 (Market) | Same application → Class 35: 'Online marketplace for fishing equipment and boats; advertising services' → Pay $250 more | IP | Critical | $250 | Mar 10 | ⬜ Not Started
65 | WEEK 7–8 | Register copyright on codebase + design | copyright.gov → $45 per work → register: app code, UI design, VisBait logo as 3 separate registrations = $135 total | IP | High | $135 | Mar 12 | ⬜ Not Started
66 | WEEK 7–8 | Have attorney review ToS + Privacy Policy | Philadelphia Bar Referral: 215-238-6333. Full review of all legal docs before media coverage or paid users | Legal | High | $1,500–3k | Mar 10–20 | ⬜ Not Started
67 | WEEK 7–8 | Get Next Insurance general liability | next.com → from ~$25/month for tech companies → get before any press release or public invitation to users | Legal | High | $300/yr | Mar 15 | ⬜ Not Started
68 | WEEK 7–8 | Have attorney finalize Operating Agreement | Even as solo founder, attorney should review. Budget $300–500. Philadelphia Bar: 215-238-6333 | Legal | High | $300–500 | Mar 15–20 | ⬜ Not Started
WEEK 9–10 · Mar 24 – Apr 6 · TESTING + PWA CONVERSION
69 | WEEK 9–10 | Convert app to Progressive Web App | Add manifest.json and sw.js to repo (already in your downloaded ZIP). Users can 'Add to Home Screen' on iOS + Android | Product | High | $0 | Mar 24–28 | ⬜ Not Started
70 | WEEK 9–10 | Run Chrome Lighthouse PWA audit | Chrome DevTools → Lighthouse → Progressive Web App. Score must be 90+. Fix any failing items | Product | High | $0 | Mar 28 | ⬜ Not Started
71 | WEEK 9–10 | Full end-to-end user flow test | New user: sign up → post catch → drop map pin → send DM → view leaderboard → edit profile. Fix every bug you find | Product | Critical | $0 | Mar 28 – Apr 4 | ⬜ Not Started
72 | WEEK 9–10 | Test on real iPhone AND Android device | Desktop Chrome is not enough. Real device testing catches real bugs. Borrow an Android if needed | Product | Critical | $0 | Apr 1–4 | ⬜ Not Started
73 | WEEK 9–10 | Load test with 250 concurrent users | loader.io free tier → simulate 250 users hitting visbait.com → Supabase free tier should handle this without errors | Security | High | $0 | Apr 4 | ⬜ Not Started
74 | WEEK 9–10 | Final OWASP ZAP scan — all features | Re-scan after all backend features are live. New features = new attack surface. Fix all High + Critical findings | Security | Critical | $0 | Apr 5 | ⬜ Not Started
75 | WEEK 9–10 | Set up data backup process | Free tier: weekly manual Supabase export to Google Drive. Paid tier ($25/mo): automatic daily backup | Security | High | $0–25/mo | Apr 5 | ⬜ Not Started
76 | WEEK 9–10 | Set up Plausible or Google Analytics | plausible.io ($9/mo, GDPR-friendly) OR Google Analytics (free, more config for GDPR). Add to index.html | Analytics | High | $0–9/mo | Apr 6 | ⬜ Not Started
WEEK 11–12 · Apr 7 – Apr 20 · BETA LAUNCH — Real users, real feedback
77 | WEEK 11–12 | Build email waitlist page at visbait.com | Simple landing page: VisBait logo, tagline, app screenshot, email input. Use Mailchimp free tier for the list | Marketing | Critical | $0 | Apr 7 | ⬜ Not Started
78 | WEEK 11–12 | Film 60-second demo video | Screen record: Feed → Map pin → post a catch → leaderboard → achievements. Add background music. This is your pitch | Marketing | Critical | $0 | Apr 7–10 | ⬜ Not Started
79 | WEEK 11–12 | Invite 50–100 beta testers | Friends, family, fishing communities you joined. NOT strangers yet. You want honest brutal feedback | Marketing | Critical | $0 | Apr 8–14 | ⬜ Not Started
80 | WEEK 11–12 | Create feedback form for beta users | Google Form: What confused you? What broke? What's missing? What did you love? Collect and read every response | Product | Critical | $0 | Apr 8 | ⬜ Not Started
81 | WEEK 11–12 | Fix top 10 issues from beta feedback | Do NOT add new features yet. Fix what is broken first. Broken > missing in user priority | Product | Critical | $0 | Apr 14–20 | ⬜ Not Started
82 | WEEK 11–12 | Join 10 Facebook fishing groups | Be an active helpful member for 3–4 weeks BEFORE mentioning VisBait. Build trust. No spam = credibility | Marketing | High | $0 | Apr 7–30 | ⬜ Not Started
83 | WEEK 11–12 | Join r/Fishing and r/bassfishing | reddit.com — 800k+ members on r/Fishing. Be genuinely helpful. Build karma before any self-promotion | Marketing | High | $0 | Apr 7 | ⬜ Not Started
WEEK 13–16 · Apr 21 – May 18 · MONETIZATION + OUTREACH
84 | WEEK 13–16 | Launch VisBait Pro subscription $7.99/mo | Stripe subscriptions → features: unlimited map pins, advanced weather, who viewed profile, no ads, priority support | Revenue | High | 2.9%+$0.30 | Apr 21–28 | ⬜ Not Started
85 | WEEK 13–16 | Add Pro badge to paying user profiles | Visible gold PRO badge on profile and posts. Social proof drives upgrades. Even 5 paying users creates FOMO | Product | High | $0 | Apr 28 | ⬜ Not Started
86 | WEEK 13–16 | Launch Elite subscription $14.99/mo | Tournament Pro application access, listing priority, detailed analytics dashboard | Revenue | Medium | $0 setup | Apr 28–May 5 | ⬜ Not Started
87 | WEEK 13–16 | Enable marketplace transactions live | 6% cut on all sales. $4.99 flat fee on boat/motor listings. Full sandbox test first, then flip to live | Revenue | High | 2.9%+$0.30 | May 1–10 | ⬜ Not Started
88 | WEEK 13–16 | Reach out to 10 fishing influencers | Target 10k–500k followers on YouTube/TikTok/Instagram. Offer free Elite in exchange for honest review post or video | Marketing | High | $0 | May 1–15 | ⬜ Not Started
89 | WEEK 13–16 | Submit to Product Hunt | producthunt.com → fishing/outdoors niche launch → write compelling founder story → good for early tech-savvy users | Marketing | Medium | $0 | May 12–15 | ⬜ Not Started
90 | WEEK 13–16 | Post in fishing communities — soft launch | Genuinely helpful post mentioning VisBait at end. Share demo video. Do not spam — share once in each group | Marketing | Medium | $0 | May 10–18 | ⬜ Not Started
JUNE 1 · PUBLIC LAUNCH DAY 🚀
91 | JUNE 1 | FEATURE FREEZE — stop adding, only fix bugs | One week before launch date. No new features. Only bug fixes and performance. This is discipline — stick to it | Product | Critical | $0 | May 25 | ⬜ Not Started
92 | JUNE 1 | Ensure site loads under 3 seconds mobile | Google PageSpeed Insights → score 90+. Compress images, lazy-load map, defer non-critical JS | Product | Critical | $0 | May 20–25 | ⬜ Not Started
93 | JUNE 1 | Prepare 5-minute demo script | Structure: Problem → VisBait solution → show Feed → Map → Achievements → Leaderboard → Marketplace → call to action | Marketing | Critical | $0 | May 25–31 | ⬜ Not Started
94 | JUNE 1 | Email entire waitlist — we are live | Mailchimp blast to everyone who signed up. Personalized if possible. Include demo video link | Marketing | Critical | $0 | June 1 | ⬜ Not Started
95 | JUNE 1 | Post launch announcement on all socials | Instagram, TikTok, YouTube, X, Facebook all go live same day. Schedule posts in advance using Buffer (free) | Marketing | Critical | $0 | June 1 | ⬜ Not Started
96 | JUNE 1 | PUBLIC LAUNCH — open signups at visbait.com | Remove any beta restrictions. Full public access. Monitor Supabase dashboard for errors. Be ready to respond fast | Marketing | Critical | $0 | June 1 | ⬜ Not Started
97 | JUNE 1 | Press outreach — fishing media | Email: BassFan.com, Wired2Fish, FishingBooker Blog, Major League Fishing media. Send press kit + demo video | Marketing | High | $0 | June 1–7 | ⬜ Not Started
98 | JUNE 1 | Monitor Supabase usage + scale if needed | Watch: DB connections, storage, auth limits. If hitting free tier limits → upgrade to Supabase Pro at $25/month | Operations | High | $0–25/mo | June 1+ | ⬜ Not Started
99 | JUNE 1 | Target: 500 registered users by June 30 | Track in Supabase dashboard. Share milestone publicly — social proof builds more signups | Marketing | High | $0 | June 30 | ⬜ Not Started
100 | JUNE 1 | Target: First paying subscriber | Even 1 paying Pro subscriber validates the business model. Celebrate it and tell the story publicly | Revenue | High | $0 | June 30 | ⬜ Not Started
POST-JUNE · Q3–Q4 2025 · MOBILE + SCALE (Only after web is proven)
101 | POST-JUNE | Validate product-market fit before mobile | 500+ active users, 10%+ returning weekly, paying subscribers? If yes → build mobile. If no → iterate first | Strategy | Critical | $0 | July 2025 | ⬜ Not Started
102 | POST-JUNE | Scope React Native mobile app | Get 3 quotes on Upwork for React Native (iOS + Android). Budget $3,000–8,000. Review portfolios carefully | Product | Medium | $3k–8k | July–Aug | ⬜ Not Started
103 | POST-JUNE | Create Apple Developer Account | developer.apple.com → $99/year → do 2–3 weeks before planned App Store submission (review takes time) | Product | Medium | $99/yr | Aug–Sep | ⬜ Not Started
104 | POST-JUNE | Create Google Play Developer Account | play.google.com/console → $25 one time → faster review than Apple (1–3 days vs 1–7 days) | Product | Medium | $25 | Aug–Sep | ⬜ Not Started
105 | POST-JUNE | Build + test React Native app | iOS + Android from one codebase. Keep feature parity with web. Do NOT add new features during rebuild | Product | Medium | $3k–8k | Sep–Oct | ⬜ Not Started
106 | POST-JUNE | Submit to Apple App Store | Requires: privacy policy URL, screenshots for all device sizes, app description, age rating, export compliance form | Product | Medium | $0 | Oct–Nov | ⬜ Not Started
107 | POST-JUNE | Submit to Google Play Store | Requires: privacy policy URL, content rating questionnaire, feature graphic. Faster review than Apple | Product | Medium | $0 | Oct–Nov | ⬜ Not Started
108 | POST-JUNE | Launch tournament feature | Requires gaming attorney sign-off + prize escrow + state-by-state research. Soft launch in FL, MN, TX first | Revenue | Medium | $1k–3k | Q4 2025 | ⬜ Not Started
109 | POST-JUNE | Hire CPA for first tax filing | Budget $300–800. Wave accounting records make this easy. Deduct: domain, software, legal fees, insurance, subscriptions | Financial | High | $300–800 | Apr 2026 | ⬜ Not Started
110 | POST-JUNE | Explore B2B data insights revenue | Sell anonymized reports to tackle brands. Aggregated only — never personal data | Revenue | Low | $0 start | 2026 | ⬜ Not Started

## June Milestone Tracker
🎯 VisBait — June 1 Launch Milestone Tracker
Every milestone below must be complete before June 1 public launch. Update Status column weekly every Monday morning.
# | Milestone | Target Date | Status | % Done | Blocker / Notes | Owner
1 | ✅ Business email set up | Done | ✅ Done | 100% | Complete
2 | ✅ Google Voice business number | Done | ✅ Done | 100% | Complete
3 | ✅ Instagram @VisBait secured | Done | ✅ Done | 100% | Complete
4 | ✅ TikTok @VisBait secured | Done | ✅ Done | 100% | Complete
5 | ✅ YouTube VisBait channel created | Done | ✅ Done | 100% | Complete
6 | X, Facebook, Pinterest handles secured | Today | ⬜ Not Started | 0% | Do right now — free and fast
7 | visbait.com domain purchased | Today | ⬜ Not Started | 0% | Namecheap ~$14
8 | USPTO trademark search cleared | Today | ⬜ Not Started | 0% | tmsearch.uspto.gov — free, 15 min
9 | PA LLC — VisBait LLC filed | Feb 2 | ⬜ Not Started | 0% | file.dos.pa.gov — $125
10 | EIN obtained from IRS | Feb 2 | ⬜ Not Started | 0% | Free, instant, irs.gov
11 | Mercury business bank account open | Feb 5 | ⬜ Not Started | 0% | mercury.com — needs LLC cert
12 | LLC Certificate received from PA | Feb 5 | ⬜ Not Started | 0% | Arrives 3–7 days after filing
13 | visbait.com live on GitHub Pages + HTTPS | Feb 5 | ⬜ Not Started | 0% | Needs domain + GitHub account
14 | Cloudflare security headers configured | Feb 7 | ⬜ Not Started | 0% | Needs Cloudflare account
15 | Privacy Policy + Terms of Service published | Feb 11 | ⬜ Not Started | 0% | termly.io — must be live before any users
16 | Supabase backend connected — real user auth | Feb 23 | ⬜ Not Started | 0% | supabase.com — free tier
17 | Real posts, feed, map pins saving to database | Mar 9 | ⬜ Not Started | 0% | Needs Supabase first
18 | USPTO trademark application filed | Mar 10 | ⬜ Not Started | 0% | $500 total — 2 classes
19 | Business insurance active (Next Insurance) | Mar 15 | ⬜ Not Started | 0% | next.com — ~$25/month
20 | OWASP ZAP security scan — all clear | Apr 6 | ⬜ Not Started | 0% | Free download — must clear High findings
21 | PWA version installable on mobile | Apr 7 | ⬜ Not Started | 0% | manifest.json + sw.js already in your ZIP
22 | Beta test with 50–100 real users complete | Apr 20 | ⬜ Not Started | 0% | Needs live site first
23 | Top 10 beta feedback issues fixed | Apr 20 | ⬜ Not Started | 0% | Needs beta feedback first
24 | Demo video filmed and ready to share | Apr 14 | ⬜ Not Started | 0% | 60 seconds, screen record
25 | Stripe payments live — marketplace ready | May 10 | ⬜ Not Started | 0% | stripe.com/connect
26 | VisBait Pro subscription tier live | Apr 28 | ⬜ Not Started | 0% | Needs Stripe first
27 | 10 fishing influencers contacted | May 15 | ⬜ Not Started | 0% | Needs demo video first
28 | Site loads under 3 seconds on mobile | May 25 | ⬜ Not Started | 0% | Google PageSpeed Insights
29 | Waitlist email blast sent to all signups | June 1 | ⬜ Not Started | 0% | Mailchimp free tier
30 | 🚀 PUBLIC LAUNCH — open signups at visbait.com | JUNE 1 | ⬜ Not Started | 0% | ALL above must be done first
31 | 500+ registered users | June 30 | ⬜ Not Started | 0% | Track in Supabase dashboard
32 | First paying Pro subscriber | June 30 | ⬜ Not Started | 0% | Validates the business model

## THIS WEEK — Action Items
⚡ VisBait — THIS WEEK Action Items ¦ Do these in order, do not skip
Complete every row marked TODAY before end of day. These are the foundation — everything else depends on them being done.
# | Task | How to Do It | When | Status | URL / Resource
1 | ✅ Business email | Already done | ✅ Done | ✅ Done | —
2 | ✅ Google Voice | Already done | ✅ Done | ✅ Done | voice.google.com
3 | ✅ Instagram @VisBait | Already done | ✅ Done | ✅ Done | instagram.com
4 | ✅ TikTok @VisBait | Already done | ✅ Done | ✅ Done | tiktok.com
5 | ✅ YouTube VisBait | Already done | ✅ Done | ✅ Done | youtube.com
6 | X (Twitter) @VisBait | x.com → Sign Up → username: visbait → use VisBait email | TODAY | ⬜ Not Started | x.com/i/flow/signup
7 | Facebook Page: VisBait | facebook.com → Create a Page → App or Software → Name: VisBait | TODAY | ⬜ Not Started | facebook.com/pages/create
8 | Pinterest Business: VisBait | pinterest.com → Sign Up → Business → Name: VisBait | TODAY | ⬜ Not Started | pinterest.com/business/create
9 | USPTO Trademark Search | Search: VisBait, Vis Bait, VizBait. Screenshot results and save them | TODAY | ⬜ Not Started | tmsearch.uspto.gov
10 | PA Business Name Search | Search VisBait — confirm it is not taken before paying $125 | TODAY | ⬜ Not Started | apps.dos.pa.gov
11 | Buy visbait.com | Search → add to cart → ENABLE WhoisGuard (free) → pay ~$14 | TODAY | ⬜ Not Started | namecheap.com
12 | File VisBait LLC | Domestic LLC → VisBait LLC → your name as agent → 'any lawful purpose' → $125 | TODAY | ⬜ Not Started | file.dos.pa.gov
13 | Get EIN from IRS | LLC → 1 member → Pennsylvania → Started new business → SCREENSHOT the EIN number | TODAY | ⬜ Not Started | irs.gov EIN application
14 | Apply Mercury bank account | Enter EIN + LLC name → upload ID → upload LLC cert when it arrives | TODAY | ⬜ Not Started | mercury.com
15 | Set up Wave accounting | Create account → will log every expense starting today | TODAY | ⬜ Not Started | wave.com

## Legal Checklist
⚖️ VisBait — Legal Battle Avoidance Checklist ¦ These will kill your company if ignored
# | Legal Risk Area | What You Must Do | Consequence If Ignored | Cost | Status | Must Do By
1 | COPPA — Children Under 13 | Add age gate at signup: 'Are you 13 or older?' → If No, deny access and delete any data. Cannot collect ANY data from under-13 users without verifiable parental consent. | FTC fines: $51,744 PER VIOLATION. 10 underage users = over $500k in fines. Actively enforced. | $0 — code only | ⬜ Not Started | Pre-launch
2 | Privacy Policy Published | Must be live BEFORE the first stranger uses the site. Cover: data collected, location, user rights, GDPR (EU users), CCPA (CA users), data deletion process, no selling of personal data. | CCPA: up to $7,500 per user. GDPR: up to 4% of annual global revenue. Class action risk. | $0 — Termly.io | ⬜ Not Started | Feb 11
3 | Location Data Consent | Explicit opt-in before storing GPS coordinates. Users must be able to delete their location data. Row-level security in Supabase. Never sell individual location records. | GDPR/CCPA violation. One EU user complaint triggers a regulatory investigation into all your data. | $0 — config only | ⬜ Not Started | Pre-launch
4 | Section 230 Protection | ToS must clearly state VisBait is a PLATFORM not a seller or publisher of user content. Use Stripe Connect — do NOT hold user funds directly (requires federal money transmitter license). | Lose Section 230: users can sue you for others' content. Hold funds without license = federal crime. | $1,500 attorney | ⬜ Not Started | Pre-launch
5 | Copyright / DMCA Process | Register DMCA agent at dmca.copyright.gov ($6/yr). Create email: dmca@visbait.com. Build documented process for receiving takedown requests and acting within 14 days. | Music labels / content owners can sue. No process = no Section 230 protection. Platform liability. | $6/yr | ⬜ Not Started | Pre-launch
6 | Tournament Prize Pools | Structure as skill-based competition NOT gambling. Hire gaming attorney before launch. Research AZ, AR, TN laws specifically — most restrictive. Escrow prize money before awarding. | Classified as illegal gambling. State AG can shut down tournament feature. Criminal charges possible. | $1,000–3,000 | ⬜ Not Started | Pre-tournament
7 | Trademark Your Name | File USPTO before any press or influencer outreach. Use ™ now (legal immediately). Switch to ® only after registration approved. Monitor for infringement quarterly. | Competitor files first → they send you a cease & desist → forced rebrand after building audience. | $500–700 filing | ⬜ Not Started | Mar 10
8 | Fishing Regulation Disclaimer | Add to EVERY map pin, advice section, and catch log page: 'Always verify local fishing regulations. VisBait is not responsible for regulatory compliance.' Short, visible, permanent. | User gets fined following app advice → lawsuit for negligent misrepresentation. Easy and free to prevent. | $0 | ⬜ Not Started | Pre-launch
9 | ADA Web Accessibility | WCAG 2.1 AA minimum: alt text on all images, minimum 4.5:1 color contrast ratio, keyboard navigable UI, no color-only information. Run free WAVE browser extension audit. | Serial ADA filers target small businesses. Average settlement: $5,000–50,000. Easy to prevent now. | $0–500 audit | ⬜ Not Started | Pre-launch
10 | Contractor Agreements | Written contract for every freelancer before they touch a line of code. Correctly classify worker: employee vs independent contractor. 1099 required for anyone paid over $600/year. | IRS audit. Back taxes + penalties. Contractor sues for employee benefits, stock, IP ownership. | $300–500 contracts | ⬜ Not Started | Before 1st hire

## Cost Summary
💰 VisBait — Cost Summary ¦ Before June vs After June
Expense | One-Time | Monthly | Annual | Notes
── REQUIRED BEFORE JUNE ──
✅ Business email (Proton/Zoho) | $0 | $0 | $0 | Free tier sufficient
✅ Google Voice | $0 | $0 | $0 | Free forever
✅ Social media handles | $0 | $0 | $0 | Instagram, TikTok, YouTube
visbait.com domain — Namecheap | $14 | — | $14 | Renews annually — enable WhoisGuard
PA LLC filing fee | $125 | — | — | One time — file.dos.pa.gov
IRS EIN | $0 | — | — | Free — irs.gov
Mercury business bank | $0 | $0 | $0 | Free, no minimums
Wave accounting | $0 | $0 | $0 | Free bookkeeping
GitHub Pages hosting | $0 | $0 | $0 | Free forever
Cloudflare CDN + security | $0 | $0 | $0 | Free tier sufficient to launch
Supabase database + auth | $0 | $0 | $0 | Free: 500MB, 50k users
OpenWeatherMap API | $0 | $0 | $0 | Free: 1,000 calls/day
Termly privacy/ToS | $0 | $0 | $0 | Free tier sufficient
DMCA agent registration | $6 | — | $6 | dmca.copyright.gov/osp
Google Workspace email | $0 | $6 | $72 | yourname@visbait.com
USPTO trademark — 2 classes | $500 | — | — | File by March 10
Business insurance — Next | $0 | $25 | $300 | Before public launch
Attorney — legal doc review | $1,500 | — | — | ToS, Privacy, Marketplace terms
Copyright registration | $135 | — | — | $45 x 3 works
SUBTOTAL — Before June | ~$2,280 | $31 | ~$392 | Most of this is legal protection
── POST-JUNE (GROWTH) ──
Plausible analytics | $0 | $9 | $108 | GDPR-friendly analytics
Supabase Pro (if you hit limits) | $0 | $25 | $300 | Only if >500MB or >50k users
Apple Developer Account | $0 | — | $99 | iOS App Store
Google Play Developer | $25 | — | — | One time
React Native developer | $3k–8k | — | — | Upwork — after web is proven
Gaming attorney — tournaments | $1k–3k | — | — | Before first tournament
CPA — annual taxes | $0 | — | $300–800 | After revenue begins
TOTAL YEAR 1 | ~$7k–14k | $65+ | ~$1,200 | Most deferred until revenue

## Quick Reference Links
📋 VisBait — Every Link You Need, Organized by Week
TODAY — FOUNDATION
✅ Google Voice (done) | voice.google.com
X (Twitter) signup | x.com/i/flow/signup
Facebook Page create | facebook.com/pages/create
Pinterest business signup | pinterest.com/business/create
USPTO trademark search | tmsearch.uspto.gov
PA business name search | apps.dos.pa.gov
Buy domain — Namecheap | namecheap.com
PA LLC filing | file.dos.pa.gov
IRS EIN application (free) | irs.gov/businesses/small-businesses-self-employed/apply-for-an-employer-identification-number-ein-online
Mercury business banking (free) | mercury.com
Wave accounting (free) | wave.com
WEEK 2 — GET SITE LIVE
GitHub (free hosting) | github.com
Cloudflare (CDN + HTTPS + WAF) | cloudflare.com
Google Maps API Console | console.cloud.google.com
OWASP ZAP (free security scan) | owasp.org/www-project-zap
WEEK 3 — LEGAL DOCS
Termly (privacy/ToS generator) | termly.io
DMCA agent registration | dmca.copyright.gov/osp
PA taxes (myPATH) | mypath.pa.gov
Google Workspace email | workspace.google.com
Philadelphia Bar Referral | 215-238-6333 ¦ philabar.org
WEEK 4 — BACKEND
Supabase (database + auth) | supabase.com
OpenWeatherMap API | openweathermap.org/api
Resend (email notifications) | resend.com
Stripe Connect (payments) | stripe.com/connect
WEEK 7 — IP PROTECTION
USPTO trademark filing | uspto.gov/trademarks/apply
Copyright registration | copyright.gov/registration
Next Insurance (business) | next.com
GROWTH
Mailchimp (email waitlist) | mailchimp.com
Plausible (analytics) | plausible.io
Product Hunt (launch platform) | producthunt.com
Buffer (social scheduling free) | buffer.com
Reddit r/Fishing (800k members) | reddit.com/r/Fishing
Reddit r/bassfishing | reddit.com/r/bassfishing
Bitwarden (free password manager) | bitwarden.com
STATUS KEY
✅ Done | Complete — mark date in Done Date column
🔄 In Progress | Actively working — update % complete
⬜ Not Started | Not begun — default state
🔴 Blocked | Cannot proceed — note the blocker